# Agenda

Discover Ashfield Board Meeting

## Date: 	Friday, 6th February 2025

| Time: | 9.00 am |
| --- | --- |
| Venue: | Meeting Room 1, Council Offices, Urban Road, Kirkby-in Ashfield/Microsoft Teams |
|  | For any further information please contact: Jake Dalton Jake.Dalton@ashfield.gov.uk 01623 457357 |

## DISCOVER ASHFIELD BOARD MEETING

| ATTENDEES |  |  |  |
| --- | --- | --- | --- |
| Name | Position on Board | Position/Organisation | Present |
| Kieran Percival | Chair | Director, Gardens of Giving CIC |  |
| Louise Knott | Vice Chair | Vice Principal, West Nottinghamshire College MA2020 Representation |  |
| Darron Ellis | Theme Lead – More to Discover | Historian, Sutton Living Memory Group |  |
| Martin Rigley OBE | Theme Lead – Succeed in Ashfield | Chief Commercial Officer Devtank Ltd. |  |
| Liz Barrett OBE | Theme Lead – Love Where You Live | Principal, Academy Transformation Trust Further Education (ATTFE) |  |
| Pete Edwards MBE | Theme Lead – Be Happy, Be Healthy | Chair, Ashfield Health and Wellbeing Partnership |  |
| Claire Hinchley | Board Member | Director Strategy and Partnerships Sherwood Forest Hospitals |  |
| Cllr Julie Gregory | Board Member | Scrutiny Representative, Ashfield District Council |  |
| Cllr Dale Grounds | Board Member | Vice-Chairman of the Council, Ashfield District Council |  |
| Cllr Matthew Relf | Board Member | Executive Lead Member for Growth, Regeneration and Local Planning, Ashfield District Council MA2020 Representation |  |
| David Williams | Substitute for Shola Olawole | Partnerships Manager North Nottinghamshire DWP |  |
| Edward Johnstone | Board Member | Assistant Principal (Development), Portland College |  |
| Graham Ward | Board Member | Chair of Board of Directors, Sherwood Forest Hospitals Trust |  |
| Holly Shuttleworth | Substitute for Paula Longden | Strategies and Partnerships Lead, Sherwood Forest Hospitals Trust |  |
| Jackie Insley | Board Member | Chief Executive Officer Citizens Advice Central Nottinghamshire |  |
| Kirsty Ellis | Substitute for Peter Gaw | Assistant CEO, Inspire: Culture, Learning and Libraries |  |
| Leanne Harwood | Substitute for Simon Cartwright | Operations Lead - Transforming Notts Together |  |
| Leanne Monger | Board Member | Interim Programme Director, Mid Notts PBP |  |
| Lee Anderson, MP | Board Member | MP for Ashfield and Eastwood |  |
| Mark Yates | Substitute | PCN Development Managers, Nottingham and Nottinghamshire ICB |  |
| Paula Longden | Substitute for Claire Hinchley | Associate Director of Strategy and Partnerships Sherwood Forest Hospitals |  |
| Peter Gaw | Board Member | Chief Executive Officer, Inspire: Culture, Learning and Libraries |  |
| Sarah Mayfield | Board Member | Director of Skills and UK College and Civic Partnerships, NTU |  |
| Sarah Speight | Observer | Deputy Vice-Chancellor & Provost, NTU |  |
| Sam Howlett | Substitute for Lee Anderson, MP | Office Manager, Ashfield & Eastwood MP’s Office |  |
| Simon Cartwright | Board Member | Chief Officer Transforming Notts |  |
| Simon Martin MBE | Board Member | Vice Principal, Academy Transformation Trust Further Education (ATTFE) |  |
| Shola Olawole | Board Member | North & East Midlands Group Performance Lead, DWP |  |
| Tim Hepke | Board Member | UK Head of Maintenance and Group Property, ITP Aero |  |
| Theresa Hodgkinson | Board Member | Chief Executive, Ashfield District Council |  |
| Una Key | Board Member | Chief Officer, Ashfield Voluntary Action |  |

| Andrea Stone | Supporting Officer | Wellbeing Manager, Ashfield District Council |  |
| --- | --- | --- | --- |
| Charles Edwards | Supporting Officer | Executive Director – Operations, Ashfield District Council |  |
| Christine Sarris | Supporting Officer | Assistant Director – Planning and Regulatory Services, Ashfield District Council |  |
| Hollie Maxwell-Smith | Supporting Officer | Discover Ashfield Lead, Ashfield District Council |  |
| Joelle Davies | Supporting Officer | Group Manager for Growth, Infrastructure and Development |  |
| John Bennett | Supporting Officer | Executive Director, Place, Ashfield District Council |  |
| Lucy Lightfoot | Supporting Officer | Regeneration Officer – Regeneration, Ashfield District Council |  |
| Melanie Wheelwright | Supporting Officer | Forward Planning & Economic Growth Team Manager Ashfield District Council |  |
| Millie Connell | Supporting Officer | Communities Graduate - Housing, Ashfield District Council |  |
| Paul Crawford | Supporting Officer | Investment Manager – Regeneration, Ashfield District Council |  |
| Paul Coffey | Supporting Officer | Interim Service Manager for Communications and Events, Ashfield District Council |  |
| Sarah Daniel | Supporting Officer | Assistant Director - Regeneration, Ashfield District Council |  |
| Jake Dalton | Supporting Officer | Communities Graduate – Regeneration, Ashfield District Council |  |
| Suzanne Morton | Observer | District Mission Enabler |  |

AGENDA

- Welcome / Introductions / Apologies - Kieran Percival

- Reflections of Previous Meeting - Kieran Percival

  - Meeting Minutes 	7 - 14

  - Action Log

- New Declarations of Interest - ALL

- Regeneration Programmes Update - Sarah Daniel 	16 - 44

  - Supplementary Documents 	45 - 48

- Cultural strategy – Nathan McNicholas

- Ashfield Podcast – Paul Coffey        49 - 50

- Theme Lead Reports - Theme Leads

  - Succeed in Ashfield - Martin Rigley

  - Love Where You Live - Liz Barrett

  - More to Discover - Darron Ellis

  - Be Healthy, Be Happy - Pete Edwards

- Board Member Updates - ALL

- Any Other Business – ALL

- Date of Next Meeting: 11th March 2026

DISCOVER ASHFIELD BOARD MEETING

Wednesday 17th December 2025

9am – 11:00am

Hybrid – Portland Room, Urban Road & Microsoft Teams

| ATTENDEES |  |  |  |
| --- | --- | --- | --- |
| Name | Position on Board | Position/Organisation | Present |
| Kieran Percival | Chair | Director, Gardens of Giving CIC |  |
| Louise Knott | Vice Chair | Vice Principal, West Nottinghamshire College MA2020 Representation | √ |
| Darron Ellis | Theme Lead – More to Discover | Historian, Sutton Living Memory Group |  |
| Martin Rigley OBE | Theme Lead – Succeed in Ashfield | Chief Commercial Officer Devtank Ltd. |  |
| Liz Barrett OBE | Theme Lead – Love Where You Live | Principal, Academy Transformation Trust Further Education (ATTFE) | √ |
| Pete Edwards | Theme Lead – Be Happy, Be Healthy | Chair, Ashfield Health and Wellbeing Partnership | √ |
| Claire Hinchley | Board Member | Director Strategy and Partnerships Sherwood Forest Hospitals |  |
| Clare Hitchings | Substitute for Tim Hepke | Communications Lead, ITP Aero |  |
| Cllr Julie Gregory | Board Member | Scrutiny Representative, Ashfield District Council | √ |
| Cllr Dale Grounds | Board Member | Vice-Chairman of the Council, Ashfield District Council |  |
| Cllr Matthew Relf | Board Member | Executive Lead Member for Growth, Regeneration and Local Planning, Ashfield District Council MA2020 Representation | √ |
| David Williams | Substitute for Shola Olawole | Partnerships Manager North Nottinghamshire DWP | √ |
| Edward Johnstone | Board Member | Assistant Principal (Development), Portland College |  |
| Gary Jordan MBE | Board Member | Community Engagement and Learning Lead, ATTFE |  |
| Graham Ward | Board Member | Chair of Board of Directors, Sherwood Forest Hospitals Trust |  |
| Holly Shuttleworth | Substitute for Paula Longden | Strategies and Partnerships Lead, Sherwood Forest Hospitals Trust |  |
| Jackie Insley | Board Member | Chief Executive Officer Citizens Advice Central Nottinghamshire |  |
| Kirsty Blyth | Substitute for Peter Gaw | Inspire: Culture, Learning and Libraries |  |
| Leanne Harwood | Substitute for Simon Cartwright | Operations Lead - Transforming Notts Together |  |
| Leanne Monger | Board Member | Interim Programme Director, Mid Notts PBP |  |
| Lee Anderson, MP | Board Member | MP for Ashfield and Eastwood |  |
| Mark Yates | Substitute | PCN Development Managers, Nottingham and Nottinghamshire ICB |  |
| Paula Longden | Substitute for Claire Hinchley | Associate Director of Strategy and Partnerships Sherwood Forest Hospitals | √ |
| Peter Gaw | Board Member | Chief Executive Officer, inspire: Culture, Learning and Libraries | √ |
| Sarah Mayfield | Board Member | Director of Skills and UK College and Civic Partnerships, NTU |  |
| Sarah Speight | Observer | Deputy Vice-Chancellor & Provost, NTU |  |
| Sam Howlett | Substitute for Lee Anderson, MP | Office Manager, Ashfield & Eastwood MP’s Office |  |
| Simon Cartwright | Board Member | Chief Officer Transforming Notts | √ |
| Simon Martin | Board Member | Vice Principal, Academy Transformation Trust Further Education (ATTFE) | √ |
| Shola Olawole | Board Member | North & East Midlands Group Performance Lead, DWP |  |
| Tim Hepke | Board Member | UK Head of Maintenance and Group Property, ITP Aero |  |
| Theresa Hodgkinson | Board Member | Chief Executive, Ashfield District Council |  |
| Una Key | Board Member | Chief Officer, Ashfield Voluntary Action | √ |
| Andrea Stone | Supporting Officer | Wellbeing Manager, Ashfield District Council |  |
| Charles Edwards | Supporting Officer | Executive Director – Operations, Ashfield District Council |  |
| Christine Sarris | Supporting Officer | Assistant Director – Planning and Regulatory Services, Ashfield District Council |  |
| Hollie Maxwell-Smith | Supporting Officer | Discover Ashfield Lead, Ashfield District Council |  |
| Joelle Davies | Supporting Officer | Group Manager for Growth, Infrastructure and Development |  |
| John Bennett | Supporting Officer | Executive Director, Place, Ashfield District Council |  |
| Lucy Lightfoot | Supporting Officer | Regeneration Officer – Regeneration, Ashfield District Council | √ |
| Melanie Wheelwright | Supporting Officer | Forward Planning & Economic Growth Team Manager Ashfield District Council |  |
| Millie Connell | Supporting Officer | Communities Graduate - Regeneration, Ashfield District Council | √ |
| Paul Crawford | Supporting Officer | Investment Manager – Regeneration, Ashfield District Council |  |
| Paul Coffey | Supporting Officer | Interim Service Manager for Communications and Events, Ashfield District Council |  |
| Sarah Daniel | Supporting Officer | Assistant Director - Regeneration, Ashfield District Council | √ |
| Jake Dalton | Supporting Officer | Communities Graduate – Regeneration, Ashfield District Council | √ |
| Joel Hough | Supporting Officer | Digital Media Assistant – Regeneration, Ashfield District Council | √ |
| Suzanne Morton | Guest | District Mission Enabler for the Methodist Church | √ |

| Agenda Item |  |
| --- | --- |
| 1 | Welcome / Introductions / Apologies – Louise Knott |
|  | - Apologies were noted for Melanie Wheelwright, Sarah Speight, Charles Edwards, Leanne Harwood, Martin Rigley, Darron Ellis. |
| 2 | Review of Previous Meeting – Pete Edward |
| a | Board Meeting Minutes |
|  | - All minutes were agreed. |
| 3 | New Declarations of Interest – ALL |
|  | - No new declarations. |
| 4. | Regeneration Programmes Update – Andrea Stone |
|  | - ADMC continuing on site. Contracts are being developed. Operator agreement will be taken to the Council’s January Cabinet. |
|  | - Ashfield construction centre is progressing but there is a delay due to the need to reinforce some of the floors. Students are due into the building around Easter |
|  | - Enterprising Ashfield has revised outputs with the six-month extension of the programme. - 25 of 26 applications were approved for the Enterprise Grants funded through UKSPF to a value of £215,863.76. - These grants were awarded across multiple industry sectors including manufacturing, retail, hospitality, leisure and healthcare. The funding will support businesses to enhance productivity and increase turnover, improve shop frontages, invest in new equipment and technology, access new markets and create new jobs. |
|  | Ashfield Financial Resilience project - Citizens Advice - The programme is prioritising residents aged 50+ in priority areas such as Leamington, Carsic and Summit. Up to November, 157 residents had been enrolled, 9 have moved into employment and 82 have developed basic skills. - The total financial gain for residents stands at £403,048 to date. |
|  | St. Mary’s Magdalene Church, Hucknall - The expression of interest to the National Heritage Lottery Fund is due to be submitted by the church for the visitor experience project. |
|  | Events Programme - All three Christmas light switch on events were held successfully, with thousands of residents showing up in Sutton, Kirkby and Hucknall. Visitors enjoyed live entertainment, funfair rides and a range of stalls with gifts, crafts food and drinks. - The annual Discover Ashfield Awards will take place at Kirkby Leisure Centre on Friday 27th February 2026. The nomination process has closed, and nominations have been reviewed. |
|  | Kings Mill Boathouse - Operator is due to open the new facility in the spring. |
|  | Sherwood Observatory - Volunteers at MSAS have recently received The King’s Award for Voluntary Service for 2025. This is the highest award a voluntary group can receive in the UK and is equivalent to an MBE. |
|  | Be Happy Be Healthy |
|  | PlayZones - The Council has received award offer letters from the Football Foundation which will be delivering the PlayZones through its contractor. These are being reviewed by ADC Legal Team. Once signed further survey work will commence in advance of planning applications being submitted. |
|  | North Kirkby Gateway - Demolition of the former factory shop on Ellis Street was due for completion by mid-December – however having received early notification of deeper foundations, completion may be delayed to January. - The planning application was submitted in late November for the new gateway building. |
|  | Green Ashfield - There is c.£1m of funding remaining, investment will be focused on reducing costs and increasing the sustainability of assets such as community buildings, car parks and parks. |
|  | Pride in Place Impact Fund – District wide - The £1.5m capital funding allocation for Ashfield is to be spent over 2025-26 and 2026-27 with £750k available per year. - Sarah outlined the proposed principles for allocating the funding which were as follows: Invest the majority of the funding into Hucknall and Rurals due to the limited opportunities for investment in these areas through other programmes. - Further investment into Sutton town centre and Stanton Hill high street to address the higher vacancy rates compared with Hucknall and Kirkby. The Kirkby area is also receiving funding through the Kirkby Pride in Place programme. - It was noted that many community facilities across the district are in poor condition, and organisations are struggling to access funds. The proposal is to introduce a grant funding programme with two tiers—approximately £20–25k and £75k. Criteria and funding levels will be developed through the DA Funding Subgroup. The expectation is that demand will exceed available funds, so the initial focus would be on Hucknall, Rurals, and Annesley, with the option to extend to Sutton if funds remain. - There have been recent requests from partners for project funding. It was suggested that these could be considered under the proposed community grant fund. - The Council has approved the implementation of HSRA powers and designated areas across the district. The initial focus will be on Sutton and Stanton Hill due to high vacancy rates. HSRA enables councils to address long-term vacant commercial properties by compelling landlords to rent out premises via an auction process. - It was confirmed that HSRA measures will only be used where landlord engagement has failed, alongside existing enforcement powers. Sutton town centre currently has a vacancy rate of 13.2%, rising to 26.1% in some areas, while Stanton Hill stands at 19.1% compared to a national average of around 13.6%. The proposal includes funding for shop front grants to support businesses in priority areas such as Portland Square, Low Street, and Outram Street. - A proposed allocation for Hucknall high street improvements was discussed. This would cover works previously included in the Hucknall Levelling Up Fund programme, which lost government funding. Planned works include upgrading paving and street furniture at the south-east end of the high street and improvements to the Market Place. - The proposed allocation for Jacksdale Skatepark would replace the ageing steel ramp system with a concrete facility. The Parish Council is working with a Nottingham skate company and local young people on the design. Funding would be match-funded through Section 106 developer contributions and parish funds. - Sarah outlined the proposed allocations: Project Proposed allocation Hucknall high street – environmental improvements £634,762 Selston High School PlayZone – match funding for £30,238 Football Foundation funding Jacksdale Skatepark £125,000 Sutton and Stanton Hill – shop front grant scheme £150,000 Community facility grant scheme £560,000 (Focus on Hucknall, Rurals, Annesley) Total £1,500,000 Decision 1 – the Board was asked to review the draft proposals, provide feedback and agree principles. - Paula Longden supported the proposal and how it has a particular focus on areas that have not been covered by previous funds. Paula questioned the support that would be offered to organisations that would be bidding for funds and the timeline for survey of community facilities. - Una Key supported the distribution of the funding. Una offered to promote the community facilities grant. Una questioned how the criteria would be decided and if metrics of usage are used, the state of the building is considered also as deteriorating facilities can impact their current usage. - Simon Cartwright questioned if there would be ongoing revenue to support the capital investment. - Peter Gaw suggested tailoring the criteria to reducing environmental impact based on sustainability and how refurbishment may be able to reduce running revenue costs. Further suggestion to use funding to support increasing accessibility of assets. Decision approved: Proposed by Una Key. Seconded by Simon Martin. - Suggestions from the board to consider sustainability and the positive impact this could have on revenue costs, accessibility, and support offered for application and the use of networks to facilitate this. |
|  | Pride in Place – Phase 1 - The Kirkby Plan - Work for Pride in Place Phase 1 (which was formerly known as the Plan for Neighbourhoods/ Long-term Plan) programme is progressing well. A 10-year regeneration plan and 4-year investment plan for Kirkby has been submitted to MHCLG following priorities identified through public consultation and engagement, and as agreed by the Kirkby Town Board. A formal update is expected from MHCLG in the new year. Two dedicated subgroups focusing on the capital and revenue elements of the fund continue to meet regularly and will now begin shaping proposals for project delivery, which is due to start from April 2026. |
|  | East Midlands Mayoral Community Development Fund - A collaborative bid, led by ATTFE has been submitted to EMCCA for approval. The bid focuses on two years of service provision and activities in the Leamington area, with some minor improvement works to Willetts Court. It will see investment shared between a number of organisations, who collectively will meet needs identified through community engagement and the 10-year action plan. - We expect to hear from EMCCA in the New Year, with delivery planned from February 2026 onwards. - The East Midlands Mayor, Claire Ward, visited Leamington on 25th November, and met a number of residents and local organisations at Willetts Court. The mayor also visited Leamington Primary Academy and received a tour by the school council. A thank you email has been received from the mayor which was included in the board paper. |
| 5 | Theme Lead Updates – Theme Leads |
| a | Succeed in Ashfield – Martin Rigley |
|  | - No update |
| b | Love Where You Live – Liz Barrett |
|  | - Liz Barrett (ATTFE): Reported positive feedback on Christmas events; Sherwood Observatory exceeded 35,000 visitors in year one and planning next-phase projects. - Programme planned to help encourage people to use the NHS service wisely. Focused on the use of pharmacies and GPs before visiting A&E particularly in the winter season when colds and flu are at an increased rate. Particularly with increased strain from resident doctors’ strikes. - ‘Stop the Bleed’ campaign surpassed 2,025 trainees by end of November. £26k raised for bleed kits which will located in defibrillator cabinets across Nottinghamshire; campaign video shown at Mansfield Town, Notts County and forthcoming Forest matches. - ‘Shop local this Christmas’ radio clip has been produced by young people and continually played on takeover radio. This was played at the board meeting. Louise Knott congratulated the students on their achievement. |
| c | More to Discover – Darron Ellis |
|  | - No updates. |
| d | Be Healthy, Be Happy – Pete Edwards |
|  | - Concerns raised in Ashfield Be Healthy, Be Happy Management Group meeting on 09/12/25 regarding Notts County Council Local Community Fund not being made available on the usual 4-year cycle, a small £5k pot announced is inadequate versus historic ~£146k countywide support (Central Notts ~£70k). Timing means potential redundancy notices for community organisations before any decision in February. - Leamington community partnership carried out an engagement walk with over thirty volunteers engaged with the residents on the estate to promote ongoing work. |
| 6. | Board Member Updates – All |
|  | - Louise Knott extended thanks to all the theme teams who dedicate their time. - Pete Edwards met on the 26th of November with Ashfield Extrusion Limited. Discussions focused on their potential participation in the board and sponsorship for the DA awards. It was a positive meeting. - DA board has been promoted in the secondary schools’ network to encourage participation at careers fair and representation on the DA board. |
|  | - The Integrated Care Board will include Derbyshire, Lincolnshire and Nottinghamshire. - Place based partnership (Mid-Notts) working on responding to ten-year heath plan and building blocks for health. |
|  | - Una Key reported that the CRAG (Coxmoor community group) Christmas event was a success with (283 attendees) with eight fledgling estate businesses; highlighted community hardship evidenced by high demand for £8 second-hand coats. |
|  | - Simon Cartwright noted that this would be his final meeting due to funding pressure and the closure of Transforming Notts Together. The board thanks Simon for his work and collaboration. |
| 7. | Any Other Business – All |
|  | - None. |
| 8. | Date of Next Meeting – 6th February 2026 |

This page is intentionally left blank

Regeneration Programmes update

The report provides an overview of progress and performance for the regeneration programmes and recommendations for allocation of funding.

1.1 Finance

Changes approved at the previous board meeting are included in annex 1.

1.2 Progress

A progress and risk-based summary for each project is provided below.

## Detailed Information

- Detailed Programme Updates

The table below provides an overview of progress and a risk-based summary for each project.

## Detailed Information

| Project | Achievements/ progress/next steps | Start/ Completion Dates | Next key Milestone | Risk Level / programme and Budget |
| --- | --- | --- | --- | --- |
| Succeed in Ashfield |  |  |  |  |
| ADMC (Automated Distribution and Manufacturing Centre) | ADMC Build: Risk levels have been elevated to high: The majority of enabling works under the preconstruction phase have been concluded. Further works on site will be progressed following the conclusion of legal agreements for S278 works, easements for utilities works and contracting arrangements. Operator: Contract negotiations are due to start with the preferred bidder. A report is scheduled to be taken to the Council’s Cabinet to approve the appointment following the conclusion of this negotiation process. | S: August 2025 C: – to be updated once the review has been concluded. | Groundbreaking: estimated March 2026 | Risk Level: High Towns Fund: £20,983,141 |
| Ashfield Construction Centre and Satellite | Refurbishment works to both the interior and exterior of the Outram Street (former Wilko’s) site are progressing well. The first phase of internal works is scheduled for completion by Easter, after which the first cohort of students is expected to move into the building. External façade works are due to be completed by the end of January. Following this, the external television screen will be installed, providing a prominent town-centre platform for promoting local community events and business advertisements. A planning application has been submitted for the installation of replacement aluminium windows. A second phase of internal refurbishment, focused on the 1930s section of the building, is due to begin after Easter. The site is anticipated to be fully operational by September. Works at the Station Park site are being finalised. | C: Autumn 2026 | VWNC: January: External façade works completed. Easter: The first cohort of students move into Outram Street site. | Risk Level: Low Towns Fund: £4,801,755 Co-funding: £1,837,500 |
| Ashfield Civil Engineering Centre | The Council’s Northern Depot refurbishment project is scheduled to be completed late 2026, after which the civils site can be handed over to VWNC. A key issue is the resolution of creating level access to the Civils site through the old salt bay and an options appraisal is due to be undertaken. Discussions are ongoing with VWNC to finalise project planning following completion of the options appraisal, with the aim of completing lease and grant funding agreements by summer. A proposal is included in section 2.1. | C: Spring 2027 | Project plans and Partnerships working with local businesses. Oct/Nov | Risk Level: Low Towns Fund: £2,101,134 Co-funding: £763,517 |
| Enterprising Ashfield – Nottingham Trent University | Reported Outputs to Date (Dec-25) Against Profile Targets: HeadStart:265 outputs / £245K - Actual: 225 / £224,173.24 - In Progress: 1 / £1,500 - Require: 39 / £19,826.76 Forecast: On Track Growth Support: 146 outputs / £NIL - Actual: 134 - In Progress: 0 - Require: 3 Forecast: On Track Specialist Growth: 35 / £232,869 - Actual: 38 / £155,814.18 - In Progress: 0 / £82,767.36 - Require: 0 / £0 Forecast: On Track R&D Collaboration: 60 outputs / £NIL - Actual: 42 - In Progress: 0 - Require: 18 Forecast: On Track Graduate Placements:50 / £220,000 - Actual: 69 / £205,000 - In Progress: 0 / £7,500 - Require: 0 / £7,500 Forecast: Low risk of having an underspend – if so, this will be re-absorbed to support the extension. 1st Time attenders’ courses:650 - Actual: 1,113 - In Progress: NIL - Require: NIL Forecast: Profile target outputs have been surpassed. Courses will continue to run up to 31st March. Returners on courses:250 - Actual: 309 - In progress: NIL - Require: NIL Forecast: Profile target outputs have been surpassed. Courses will continue to run up to 31st March. | C: March 2026 |  | Risk Level: No Risk Towns Fund: £3,845,000 Co-funding: £3,746,867 |
| Enterprise Development Grants | 25 of 26 applications were approved to a value of £215,863.76. As of 21/1/26 we have processed £157,297.28 of grant claims and have £58,566.49 to process before 28th Jan. There is currently an underspend of £338.74 | 23rd Apr-25 to 31st Oct-25 closing date for applications | Monitor Claims to draw down awarded grants in full by 28th Jan-26 | Risk Level: Low UKSPF: £215,863.76 |
| Test Trading Opportunities (Markets) | 3 grants have been awarded. Totalling £1,414.14. | 23rd Apr-25 to 31st Oct. | COMPLETED | Risk Level: Low |
| High Street Business Support | This project aims to support 28 businesses and is being delivered by two suppliers: - Save The Highstreet are delivering in Sutton & Kirkby with a target of 12 businesses to support. To date 6 outputs have been reported. This data comes from Nov-25 report. No outputs were reported in DEC-25 as this is the busiest trading period for this project target clients. Officers are closely monitoring performance and have set a goal for 4 outputs to be achieved in Jan-26 to ensure we remain on track. Failure to do so could result in a contract variation or we could agree to extend delivery Cliffen Consulting are delivering in Hucknall & the rural areas with a target of 16 businesses to support. To date 12 outputs have been reported. This data is from Dec-25. Officers have been advised there will be at least 2 more in Jan-26 report totalling 14. Officers are now monitoring the number of hours completed with enrolled clients as we must ensure 6 hours per client by 31st March. | 23rd Apr-25 to 31st March 2026 | Monitoring of delivery up to Jan-26 | UKSPF: £19,900K Risk Level: Kirkby & Sutton – medium Risk level: Hucknall & Rurals – Low |
| Small Business Membership | The Federation for Small Businesses (FSB) are delivering this to 60 businesses. 23 memberships have so far been achieved (Dec-25 Report.) Officers are supporting FSB to engage with partners to increase engagement with local SMEs. We have also requested an FSB achieve a significant number of outputs in January report (at least17 outputs) to bring this project back on track. Failure to do so will lead to a contract variation to reduce risk of underspend or we can allow an extension to the closing date. | 1st Sept-25 to 31st March 2026 | Monitoring of delivery in Nov-Dec-25 reports | Risk Level: Medium UKSPF: £9,950 |
| Take over Radio Project | Sutton Youth Radio were due to deliver 24 local radio promotional features to encourage trade in December for Jacksdale and Stanton Hill. They delivered 36 promotional broadcasts which included 10 businesses as flows: 6 in Jacksdale and 4 in Stanton Hill. | 15th Dec 2025 to 31st Dec 2025. | COMPLETED | Risk Level: No Risk UKSPF £1,920 |
| Ashfield Transform your Future programme (Economically Inactive Support) | This employability programme supports economically inactive residents, prioritising young people aged 16-24 that are not in employment, education or training (NEET), and in priority areas such as Leamington, Carsic and Stanton Hill. Up to December, 142 residents have enrolled onto the programme (46% are aged 16-24 NEET), from which 24 have moved into employment and 18 have moved into education / training. During January-March, they will be shifting their focus to support young people, and will be engaging with residents in the priority wards. | To be completed by 31st March 2026 | Monitoring of delivery | Risk Level: Low £80,000 UKSPF |
| Ashfield Financial Resilience project - Citizens Advice | The programme is prioritising residents aged 50+ in priority areas such as Leamington, Carsic and Summit. Up to December, 191 residents from 169 households have been enrolled, 9 have moved into employment and 82 have developed basic skills. They are also signposting and referring participants to employment and skills providers. During January-March, they will be shifting their focus to support people in priority wards that currently have low engagement. The total financial gain for residents stands at £403,048 to date. | To be completed by 31st March 2026 | Monitoring of delivery | Risk Level: Low UKSPF: £32,609 |
| Science, Technology, Engineering, and Maths (STEM) Careers Education for Stakeholders project “Ashfield STEM Boost” | The Threes Club Services Ltd are delivering this contract which supports employees from key education and skills stakeholders understand the STEM labour market, giving them the confidence to promote these opportunities with their service users. Up to December, 3 sessions have been delivered to 2 organisations, in which 35 STEM professionals attended. They are running Ashfield STEM Connect networking events, which brings together local STEM educators and employers, with the latest event held on 29th January. | 31st March 2026 | Monitoring of delivery | Risk Level: Medium UKSPF: £40,000 |

| Project | Achievements/ progress/next steps | Start / Completion Dates | Next key Milestone | Risk Level / programme and Budget |
| --- | --- | --- | --- | --- |
| More to Discover |  |  |  |  |
| St. Mary’s Magdalene Church, Hucknall | The expression of interest to the National Heritage Lottery Fund is due to be submitted by the church for the visitor experience project. | TBC |  |  |
| Ashfield Creates | Ashfield Creates is a 2.5-year programme (2024-2027), with an aim to increase community engagement in arts and culture. Nonsuch Studios are delivering this programme and are facilitating creative activities at community events such as Ashfield Show and live events at venues across Ashfield. 45 events have been delivered to date. Recent events include button making, ceramics, folk festivals, snowflake making, and craft fairs. Nonsuch are finalising the 3rd round of community commissions and funding which can be used to support creative ideas and events. A Cultural Strategy has been prepared which will be presented at the board meeting. Ashfield Arts Partnership, a subgroup of Discover Ashfield is overseeing delivery of the programme, and the next meeting will be in March 2026 to review progress. |  |  | Risk Level: Low Arts Council: £1,000,000 UKSPF: £10,000 |
| Events Programme | The main events programme for 25/26 has now concluded. A proposal has been included in section 2.1. The annual Discover Ashfield Awards will take place at Kirkby Leisure Centre on Friday 27th February. Over 50 people, organisations and groups have been shortlisted for an award. | C: March 2026 | DA Awards February 2026 | Risk Level: Low UKSPF: £27,000 |
| Cornerstone Theatre | Since practical completion in July 2025, the venue has welcomed over 1,717 users, of which 1,177 were external customers, demonstrating strong early demand. The theatre’s official opening is scheduled for March, a programme of soft-launch events is underway to test operational processes, logistics, and technical equipment. Ticket sales for the programme arranged by an external promoter have been lower than anticipated and the approach is being reviewed with the Advisory Board which is due to start meeting again soon. The Council is supporting with additional marketing and an offer of business support. The remaining snagging items are being finalised with the contractor Miller Knight. | S: June 2024 C: March 2026 | Autumn 2025 events programme | Risk Level: Low FHSF: £2,347,118 Towns Fund: £1,172,067.81 UKSPF: £66,866 |
| Cycling and walking routes | A recent procurement did not appoint a contractor due to costs exceeding expectations. The specification has been revised and preparation are underway for a new tender due to be published in February through an Open Market opportunity. | C: Sept 2026 | Award of contract Spring 2026 | Risk Level: Low Towns Fund: £1,936,280 Co-funding: £45,000 |
| Kings Mill Boathouse | The kitchen installation has been completed and handover to the Council has taken place. Risk remains elevated due to delays in finalising the lease with the operator which is currently being negotiated. The operator is due to open the facility in the spring. | TBC | Operator Opening | Risk Level: High Towns Fund: £3,352,000 Co-funding: £648,000 |
| ‘Now and then’ heritage | Exhibition materials created through the recent workshops are now being prepared for display at Hucknall and Skegby Libraries throughout February and March. A photography workshop was held on 15th January in Selston, and the digital exhibition is currently in development ahead of its launch on 14th March. The exhibitions celebrate Hucknall, Skegby and Selston, showcasing contemporary photography inspired by images from Inspire’s heritage collections. The work has been created by adults from the local communities in collaboration with professional photographer Neil Pledger. Alongside the photography, the live exhibitions in Hucknall and Skegby will also feature artwork based on historical maps, created by children from the communities working with artist Edwina King. The official celebration event for Hucknall, Skegby and Selston: Then and Now will take place at Hucknall Library on 14th March. | S: July 2025 C: March 2026 | Hucknall Library Exhibition 3rd Feb – 29th March Skegby Library Exhibition 24th Feb – 22nd March Celebration Event 14th March 2026, Hucknall Library 12-2pm | Risk Level: Low UKSPF: £15,000 |
| Hucknall Library | Items identified within the Hucknall physical collection have now been preserved by conservators, ensuring they can be safely accessed. These include several significant pieces relating to Eric Coates. The new Nottinghamshire Digital Archives online platform is currently in its testing phase and, once launched, will open up access to items that were previously difficult to view due to fragile physical condition or translation challenges, for example. Additional furnishings have been ordered to complete the refurbishment of the heritage area at the library. The official celebration event at Hucknall Library on 14th March will offer the community an opportunity to explore the newly enhanced heritage resources, including the Nottinghamshire Digital Archive platform. The event will also feature an interactive family workshop led by artist Edwina King. | S: July 2025 C: March 2026 | Exhibit new collections online. March 2026 Celebration Event March 2026 | Risk Level: Low UKSPF: £33,500 |
| Sherwood Observatory | Advanced group bookings continue to perform strongly, with all evening slots for the winter seasons now fully booked. Marketing activity has maintained strong visibility, with newsletter subscriptions rising to 9,363, a shortlist placement in the Nottinghamshire Tourism Awards, and Facebook followers reaching 16,600, supported by increased physical leaflet distribution. | S: July 2025 C: March 2026 | Continued monitoring and evaluation on outputs and outcomes. | Risk Level: Low UKSPF: £13,695 |

| Project | Achievements/ progress/next steps | Start/ Completion Dates | Next key Milestone | Risk Level / programme and Budget |
| --- | --- | --- | --- | --- |
| Be Healthy Be Happy |  |  |  |  |
| Kirkby Sports Hub | The new pavilion foundations have been cast and brickwork up to DPC level has commenced, the slab was slightly delayed due to ground conditions and will incur additional cost. The bowls pavilion foundations have been delayed due to finding underground land drains which required a design solution and will incur additional cost. Anti-social behaviour is still high; a 2nd security guard was instructed over the Christmas break. The Council’s Community Protection team are looking into ways to reduce the issues to help mitigate any cost impact of the additional security required. | S: 20th October 2025 C: 10th August 2026 | FF Grant Agreement Signing | Risk Level: Medium Towns Fund: £2,745,677 Co-funding: £289,000 |
| Sutton Lawn Sports Hub | Issues remain regarding the legal agreements between ATT and ADC, until these are resolved the main contractor appointment (pavilion and car park) cannot be signed, there is a 6-week lead in to start works after the contract signing. We are awaiting information from the Football Foundation to progress the delivery of the two 3G pitches, the Football Foundation Grant Agreement cannot be signed until this is resolved. After this the ADC/ATT agreements need to be updated. Retendering the works may result in a cost increase. The decision on whether to enter into the grant agreement with the Football Foundation is being taken to the Council’s Cabinet in February. | S: Mar/Apr 2026 C: Jan 2027 Subject to costs & FF sign off | Sign legal agreements between ATT/ADC. Sign the Pavilion and Car Park Contract (and ATT legal agreements). Resolve 3G pitch procurement route. Sign FF grant offer letter. Update legal agreements between ATT/ADC. | Risk Level: High Towns Fund: £2,918,633 Co-funding: £2,271,234 Other: £55,000 |
| Albert Street Recreation Ground | Two proposals are included for this project in section 2.1. to extend the completion date and increase funding. Legal issues regarding land status are causing a delay in signing the contract and progressing works. | S: July 2025 C: Sept 2026 | Inspection of existing play equipment. Final design completion. | Risk Level: Medium UKSPF £75,0000 Pending additional £10,000 |
| PlayZones Stamper Rec., Cowpasture Rec., Sutton, Morven Park, Kirkby, Titchfield Park, Hucknall and Selston High School | The Council has received award offer letters from the Football Foundation which will be delivering the PlayZones through its contractor. The review by Legal continues. Once accepted, the project will move to final design and requesting planning permissions. | S: Summer 2026 C: January 2027 £0 |  | Risk Level: Low |
| Community Grants | The following organisations have been awarded funding: - Gardens of Giving - ATTFE - Citizens Advice - Kingsmill Community First Responders - Thrive Together Consultancy - Muddled Minds CIC - Volunteer it Yourself - Hucknall Engage Ltd - Portland Charity - Ashfield Spartans Boxing Academy - Active Minds Nottingham - Open Door 1 - OT Fundraisers Grant Funding Agreements have been finalised. Monitoring is being collected for all projects, which are on track to deliver their projects as agreed. A proposal is included for this project in section 2.1 | June 25 – March 26 | Project completion by Feb 26. | Risk Level: Low UKSPF: £120,000 |

| Project | Achievements/ progress/next steps | Start/ Completion Dates | Next key Milestone | Risk Level / programme and Budget |
| --- | --- | --- | --- | --- |
| Town Centres & High Streets |  |  |  |  |
| High Street Property Fund | The learning outcomes and associated construction project work has been finalised. Risk: has been elevated: The project start date has slipped due to complexities around securing a delivery agreement with Vision West Notts College. Options are being progressed to secure the agreement with a revised estimated start of June 2026. | S: EST: June. 2026 C: June 2027 | Skills delivery Summer 2026. | Risk Level: Medium Towns Fund: £173,933 Co-funding: £100,000 |
| Hucknall |  |  |  |  |
| Central Walk & Chapel Street – public realm improvements | Planning was approved for both sites on 10th December. Occupier licences to carry out works are in progress. Section 278 works application has been submitted – which required an alteration to the steps. We have a recommended contractor and are seeking internal approvals to progress the contract award. The main works are due to start on site February/March 2026. Murals/street art will follow on from the main works. Two proposals are included for this project in section 2.1 to extend the timeline and increase funding. | S: Feb/Mar 2026 C: July/August 2026 | Award Tender. Legal Agreements with Tenants. Sign construction contract Jan/Feb 2026. | Risk Level: Low UKSPF: £313,265 Co-funding: £175,619 Section 106: £214,800 |
| Kirkby |  |  |  |  |
| North Kirkby Gateway | Demolition of the former factory shop on Ellis Street reached practical completion on 16th January. The RIBA 3 Gateway has been approved - The planning application was submitted in late November. Options for the end use/operator strategy are under review to ensure the best economic and social value are achieved. | C: August 2027 | Design team re-mobilised and develop designs to RIBA 4 | Risk Level: Low Monitor delays and seek to progress the design and construction phases. Towns Fund: £8,729,648 Co-funding: £5,140,999 |
| West Kirkby Gateway | Planning permission was agreed on 10th December, and the decision notice has now been received. The Project Board approved RIBA 4 cost plan on 12th December to proceed to construction. Contract documents are being progressed for the main works in preparation of work commencing although start on site has slipped slightly to aid further time to complete the planning and contract documentation. Subject to planning pre-commencement and BAPA approvals the start date is late March / early April. | S: April 2026 C: April 2027 | Breaking Ground, April 2027 | Risk Level: Low Towns Fund: £3,558,041 Co-funding: £2,357,131 (reduced from approved £3,920,000) |
| Sutton |  |  |  |  |
| Portland Square & Fox Street | Fox Street is the permanent home of Sutton’s Outdoor market, taking place every Monday and is used as a car park during the rest of the week with two hours free parking. | C: Oct 2025 | New Market to be marketed | Risk Level: Low Portland Square: Towns Fund: £1,448,352 Co-funding: £405,000 Fox Street: FHSF: £611,088 Co-funding: £70,912 |
| Low Street | The projects to refurbish and repurpose two properties on Low Street have been completed. The team is reviewing the discharge of conditions relating to managing acoustic levels on 9-11 Low Street and will introduce minor amendments to the scheme to improve the building. | Projects Completed |  | Risk Level: Low FHSF: £1,750,000 Co-funding: £647,933 |
| Library Innovation Centres - Kirkby & Sutton | Inspire have confirmed the revised delivery timetable for the Sutton investment. The project will now progress early February. | S: Feb 2026 C: Oct 2026 | Draft Design Plans Feb 2026 | Risk Level: Low Towns Fund: £737,478 Co-funding: £113,000 |
| Stanton Hill Investment Plan | The community allotment has now been cleared, and procurement is underway to appoint a fencing contractor. Planning permission has been obtained for the fencing replacement. The community have recently formed a local committee to manage the space which will be leased from East Midlands Homes. A community event is being planned to launch the allotment. Three artists have expressed their interest in the mural, and an artist has been appointed, and the design process has commenced. A bench is due to be installed in the community garden. Opportunities to upgrade shop frontages and work with vacant properties is ongoing. A proposal is included for this project in section 2.1. | 1 April 2025 – 31 March 2026 (UKSPF) | Lease arrangements for the allotment Fencing of the allotment Community launch event Agreement of mural design Bespoke support/grant for landlords and businesses | Risk Level: Medium UKSPF: £40,000 Section 106: £199,940.39 |

| Project | Achievements/ progress/next steps | Start/ Completion Dates | Next key Milestone | Risk Level / programme and Budget |
| --- | --- | --- | --- | --- |
| Green Ashfield |  |  |  |  |
| Green Ashfield | There is c.£1m of funding remaining, investment will be focused on reducing costs and increasing the sustainability of Council assets such as community buildings, car parks and parks. Site visits are underway to assess the buildings in the programme. | TBC | Retrofit PR – Carbon saving to project sites | Risk Level: Medium Towns Fund: £2,198,048 Co-funding: £800,000 |

2.1 Proposals

2.11 Programme Extension UKSPF 2025-26

In December, MHCLG announced an extension to the UKSPF 2025–26 spend deadline to 30th September. However, additional guidance issued by EMCCA encourages local authorities to maximise spend by 31st March wherever possible.

To ensure both maximum spend and impact, it is proposed that the following projects are approved for an extension in line with the revised UKSPF spend deadline:

- Stanton Hill Investment Plan

- Central Walk and Chapel Street Public Realm Improvements

- Albert Street Recreation Ground

- Community Grants (specifically the grant awarded to Citizens Advice to support delivery of the Financial Resilience Programme)

Decision 1: The Board is asked to consider and approve the proposed deadline extensions for the projects listed above.

2.12 Administration Costs – UKSPF 2025/26

A 4% management fee totalling £52,208 (up to £4,634 capital and £47,574 revenue) is available to support the development and administration of the programme and was approved by the Board at the beginning of the programme. Following clarification on the capital/revenue apportionment, it is expected that £18,240 of these costs will need to be met through revenue underspends across the programme.

Decision 2: The Board is asked to consider and approve up to £18,240 of revenue management costs be met from any underspend within the revenue project budgets, with flexibility regarding the specific source.

2.13 Reallocation of remaining UKSPF capital funds

There is £27,739 of unallocated capital funding remaining within the UKSPF programme. This includes £9,500 returned from the Inspire Hucknall project and £18,239 no longer claimable as administration costs based on mid-year reporting guidance.

It is recommended that the remaining £27,739 be allocated as follows:

- Central Walk and Chapel Street Public Realm Improvements: £17,739

- Albert Street Recreation Ground: £10,000

Board approval is also requested to allow flexibility to reallocate the funds between these two projects as required.

Decision 3: The Board is asked to consider and approve the reallocation of £27,739 to Central Walk and Chapel Street and Albert Street Recreation Ground and to delegate flexibility to adjust the distribution of funds between these two projects as necessary to accommodate final project budget requirements.

2.14 ADMC Pre-opening Support (UKSPF)

An underspend of approximately £6,000 is anticipated for this project. It is proposed that any remaining funds, following completion of the allocated UKSPF activity in March 2026, be reallocated to support the ADMC capital project.

Decision 4: The Board is asked to consider and approve the reallocation of all remaining funds to the ADMC Capital Project.

Ashfield Show (UKSPF)

Following reconciliation of the Ashfield Show budgets, £1,882.97 has been identified as available funding. It is proposed that this be reallocated to the UKSPF Events Budget to support ongoing commitments.

Decision 5: The Board is asked to consider and approve the reallocation of £1,882.97 to the UKSPF Events Budget.

2.16 Extend the scope of the Civil Engineering Centre – Towns Fund

Approval is sought from the Board for an agreement in principle to extend the scope of the project, within the existing allocated Civils budget, to support the development and delivery of the College’s vehicle maintenance provision at the Council’s Depot site. This extension will contribute to enhanced learning outcomes in line with the project’s objectives. A further proposal setting out the financial implications will be presented to the Board in due course.

Decision 6: The Board is asked to consider and approve in principle, the extension of the Civils project scope to incorporate the development and delivery of VWNC vehicle maintenance provision at the Depot site, subject to a full financial proposal being brought forward for consideration to a future Board meeting.

2.2 Monitoring and Evaluation

A monitoring and evaluation report for Pride in Place Impact Fund is currently being developed and is due to be submitted by 16th February.

The next formal monitoring and evaluation for Towns Fund and UKSPF will take place in spring.

2.3 Communications

Communication activities during the last period were as follows:

- Cornerstone Refurbishment – EEM Building Communities Awards Nomination.

- Cornerstone – Programme Update

- Kings Mill Reservoir boathouse update

- Sherwood Observatory – 1 year opening update

2.4 Risk registers

The risk registers for the programmes are included in the annexes to the report. A comparison to risk from the last assessment is provided in the commentary.

2.5 Procurement

The procurement activities for this period are detailed in Annex 3.

3.0 	Pride in Place

Pride in Place Impact Fund - District wide

The Pride in Place Impact Fund programme for Ashfield is progressing, with priority projects agreed at December’s board meeting.

Key highlights:

- Funding Strategy: Most funding will support Hucknall and rural areas (Jacksdale, Selston), where alternative funding is limited. Additional targeted investment will address high vacancy rates in Sutton town centre and Stanton Hill.

- Community Grants: A two-tier grant scheme (£20–25k and £75k) is being developed to improve poor‑condition community facilities. Early investment will focus on Hucknall, rural settlements, and Annesley.

- High Street Regeneration: Newly approved High Street Rental Auction powers will help bring long‑term vacant units back into use, prioritising Sutton and Stanton Hill. Shop front grants will support improvements in key locations such as Portland Square, Low Street, and Outram Street. Hucknall town centre will also see paving, street furniture and Market Place upgrades.

- Public Space Improvements: Planned investments include redeveloping Jacksdale’s skatepark (with S106 and Parish funding) and match funding a Football Foundation PlayZone at Selston High School.

The next stage will involve the development of detailed delivery plans.

Pride in Place - Kirkby

We are awaiting formal feedback from MHCLG. In the meantime, two dedicated subgroups supported by Council officers are progressing early project proposals in line with the proposed investment and regeneration plan.

Key emerging priorities include:

- Community Infrastructure Mapping (Capital): Mapping existing community facilities to inform a capital Community Grant Scheme focused on refurbishing and improving buildings and spaces in poor condition.

- Digital Inclusion (Capital): Developing a digital inclusion project aimed at improving educational attainment through enhanced access to digital skills, devices and connectivity.

- Community Grants for Projects and Activities (Revenue): Scoping a revenue‑funded programme to support local projects, events and activities that strengthen community engagement and participation.

4.0 East Midlands Mayoral Community Development Fund

A collaborative bid, led by ATTFE has been submitted to EMCCA for approval.  The bid focuses on two years of service provision and activities in the Leamington area, with some minor improvement works to Willetts Court.  It will see investment shared between a number of organisations, who collectively will meet needs identified through community engagement and the 10-year action plan.

The outcome of the bid is expected imminently.  EMCCA’s guidance states a project start date of 2nd February, with decisions made and communication sent by 31st January 2026.

Annex 1 – FHSF approved budgets.

| Project | RDEL/CDEL | 21/22 (£) | 22/23 (£) | 23/24 (£) | 24/25 (£) | 25/26 (£) | Total (£) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FHSF Sutton Academy Theatre / Cornerstone | RDEL (Revenue) | - | - | - | - | - | - |
|  | CDEL (Capital) | 48,545 | 143,287 | 2,155,287 |  |  | 2,347,118 |
|  |  | 48,545 | 143,287 | 2,155,287 | - | - | 2,347,118 |
|  | Co-funding |  |  | 100,000 |  |  | 100,000 |
|  | TOTAL |  |  |  |  |  | 3,183,385.81 |
| FHSF High Pavement | RDEL |  |  |  |  |  | - |
|  | CDEL | 988,342 | 148,812 | 514,511 |  |  | 1,651,665 |
|  | Sub Total | 988,342 | 148,812 | 514,511 | - | - | 1,651,665 |
|  | Co-funding |  | - | 937,289 |  |  | 937,289 |
|  | Total |  |  |  |  |  | 2,588,954 |
| FHSF Low Street 9-11 and No 14 | RDEL |  |  |  |  |  |  |
|  | CDEL | 86,920 | 1,081,310 | 581,770 |  |  | 1,750,000 |
|  | Co-funding |  |  | 647,933 |  |  | 647,933 |
|  | Total |  |  |  |  |  | 2,397,933 |
| FHSF Fox Street pop- up food court and car park | RDEL |  |  |  |  |  |  |
|  | CDEL | 67,314 | 44,397 | 419,378 |  |  | 531,088 |
|  | Co-funding | - |  | 70,912 |  |  | 70,912 |
|  | Total |  |  |  |  |  | 602,000 |

Annex 2 - Towns Fund DA Board approved budgets.

| Project | RDEL/CDEL | 21/22 (£) | 22/23 (£) | 23/24 (£) | 24/25 (£) | 25/26 (£) | Total (£) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TF-01 Ashfield Civil Engineering Centre | RDEL (Revenue) | - |  |  |  |  | - |
|  | CDEL (Capital) | 6,902 | 46,865 | 2,047,367 | - |  | 2,101,134 |
|  | Sub Total | 6,902 | 46,865 | 2,047,367 | - | - | 2,101,134 |
|  | Co-funding |  | 453,017 | 250,000 | 60,500 |  | 763,517 |
|  | TOTAL |  |  |  |  |  | 2,864,651 |
| TF-02 Ashfield Construction Centre | RDEL | - | - | - | - | - | - |
|  | CDEL | 14,746 | 21,377 | 733,077 | 4,032,555 |  | 4,801,755 |
|  | Total | 14,746 | 21,377 | 733,077 | 4,032,555 | - | 4,801,755 |
|  | Co-funding |  | - | 1,837,500 | - | - | 1,837,500 |
|  | TOTAL |  |  |  |  |  | 6,639,255 |
| TF-03 Automated Distribution and Manufacturing Centre | RDEL | - | - | 500,000 | 375,000 | 125,000 | 1,000,000 |
|  | CDEL | 17,035 | 153,724 | 19,079,241 | 233,141 | - | 19,983,141 |
|  | Sub Total | 17,035 | 153,724 | 19,579,241 | 608,141 | 125,000 | 20,983,141 |
|  | Co-funding |  |  |  | 467,000 | 934,000 | 1,401,000 |
|  | TOTAL |  |  |  |  |  | 22,384,141 |
| TF-04 Cycling and Walking Routes | RDEL | - | - | - | - | - | - |
|  | CDEL | 1,142 | 30,000 | 1,808,138 | 97,000 | - | 1,936,280 |
|  | Total | 1,142 | 30,000 | 1,808,138 | 97,000 | - | 1,936,280 |
|  | Co-funding |  |  | - | 45,000 |  | 45,000 |
|  | TOTAL |  |  |  |  |  | 1,981,280 |
| TF-05 Enterprising Ashfield | RDEL | 2,344 | 681,553 | 1,360,103 | 985,000 | 816,000 | 3,845,000 |
|  | CDEL | - | - | - | - | - | - |
|  | Sub Total | 2,344 | 681,553 | 1,360,103 | 985,000 | 816,000 | 3,845,000 |
|  | Co-funding |  |  |  |  |  | 3,746,867 |
|  | TOTAL |  |  |  |  |  | 7,591,867 |
| TF-06 Green Ashfield | RDEL | - | - | - | - | - | - |
|  | CDEL | 1,142 | 114,457 | 1,684,401 | 398,048 |  | 2,198,048 |
|  | Sub Total | 1,142 | 114,457 | 1,684,401 | 398,048 | - | 2,198,048 |
|  | Co-funding |  |  | 2,812,134 | 317,167 | - | 3,129,301 |
|  | TOTAL |  |  |  |  |  | 5,327,349 |
| TF-07 High Street Property Fund | RDEL | - | - | - | - | - | - |
|  | CDEL | 18,265 | 4,631 | 640,037.19 |  |  | 523,933 |
|  | Sub Total | 18,265 | 4,631 | 640,037.19 | - | - | 522,933 |
|  | Co-funding |  |  | 100,000 |  |  | 100,000 |
|  | TOTAL |  |  |  |  |  | 623,933 |
| TF-08 Kings Mill Reservoir Leisure Development | RDEL | - | - | - | - | - | - |
|  | CDEL | 23,196 | 459,422 | 2,059,125 | 810,257 |  | 3,352,000 |
|  | Sub Total | 127,000 | 2,414,743 | 2,414,743 | 2,414,743 |  | 3,352,000 |
|  | Co-funding |  |  | 192,000 | 456,000 |  | 848,000 |
|  | TOTAL |  |  |  |  |  | 4,200,000 |
| TF-09 Kingsway Sports Hub | RDEL | - | - | - | - | - | - |
|  | CDEL | 5,640 | 87,059 | 1,898,977 | 500,000 | 406,000 | 1,991,676 |
|  | Total | 5,640 | 87,059 | 1,898,977 | 500,000 | 406,000 | 1,991,676 |
|  | Co-funding | 39,000 |  |  | 250,000 |  | 289,000 |
|  | TOTAL |  |  |  |  |  | 3,240,176 |
| TF-10 Library Innovation Centres | RDEL | - | - | 48,000 | 51,000 | 51,000 | 150,000 |
|  | CDEL |  | 3,375 | 509,625 | 38,000 | 36,478 | 587,478 |
|  | Sub Total | - | 3,375 | 557,625 | 89,000 | 87,478 | 737,478 |
|  | Co-funding |  |  |  | 113,000 |  | 113,000 |
|  | TOTAL |  |  |  |  |  | 850,478 |
| TF-11 North Kirkby Gateway | RDEL | - | - | - | 90,000 | 90,000 | 180,000 |
|  | CDEL | 7,935 | 83,605 | 1,520,583 | 3,330,797 | 3,786,727 | 8,729,648 |
|  | Sub Total | 7,935 | 83,605 | 1,520,583 | 3,420,797 | 3,876,727 | 8,909,648 |
|  | Co-funding |  |  |  | 2,155,000 | 2,985,999 | 5,140,999 |
|  | TOTAL |  |  |  |  |  | 14,050,647 |
| TF-12 Portland Square Refurbishment | RDEL | - | - | - | - | - | - |
|  | CDEL | 65,000 | 400,000 | 903,352 | - | - | 1,368,352 |
|  | Total | 65,000 | 400,000 | 903,352 | - | - | 1,368,352 |
|  | Co-funding | - |  | 136,000 | 269,000 |  | 405,000 |
|  | TOTAL |  |  |  |  |  | 1,773,351 |
| TF-14 Science Discovery Centre & Planetarium | RDEL | - | - | - | - | - | - |
|  | CDEL | 149,500 | 385,786 | 1,554,714 | 208,004 |  | 2,298,004 |
|  | Total | 149,500 | 385,786 | 1,554,714 | 208,004 | - | 2,298,004 |
|  | Co-funding | - | 29,000 |  | 956,000 |  | 985,000 |
| LUF- Science Discovery Centre | CDEL | - | 250,000 | 1,425,000 | 1,425,000 | - | 3,100,000 |
|  | Total |  |  |  |  |  | 6,333,004 |
| TF-15 Sutton Lawn Sports Hub | RDEL | - | - | - | - | - | - |
|  | CDEL | 5,661 | 113,904 | 651,435 | 2,047,633 | 200,000 | 3,018,633 |
|  | Total | 5,661 | 113,904 | 651,435 | 2,047,633 | 200,000 | 3,018,633 |
|  | Co-funding |  |  | 107,974 | 264,000 | 1,846,854 | 2,218,828 |
|  | TOTAL |  |  |  |  |  | 5,237,461 |
| TF-16 Visitor Digital Offer | RDEL | - | - | - | - | - | - |
|  | CDEL | 11,474 | 58,539 | 144,797 |  |  | 214,809 |
|  | Total | 11,474 | 58,539 | 144,797 | - | - | 214,809 |
|  | Co-funding |  |  | 45,000 |  |  | 45,000 |
|  | TOTAL |  |  |  |  |  | 259,809 |
| TF-17 West Kirkby Gateway | RDEL | - | - | - | - | - | - |
|  | CDEL | 6,908 | 250,128 | 959,965 | 2,741,041 |  | 3,958,041 |
|  | Total | 6,908 | 250,128 | 959,965 | 2,741,041 | - | 3,958,041 |
|  | Co-funding |  |  |  | 3,920,000 |  | 3,920,000 |
|  |  |  |  |  |  |  | 7,878,041 |
| TF 18 Cornerstone Theatre | CDEL | - | 1,496 | - | 1,110,571 | - | 1,112,067 |
|  | TOTAL | - |  | - |  |  | 1,112,067 |

Annex 3 – Recent Procurement Activity

| Regeneration | Partial demolition of existing sports pavilion and construction of new changing rooms and associated external works. Demolition of existing bowls building and construction of new bowls pavilion and associated external works. Public car park extension and refurbishment. Drainage works to existing football pitches. Conversion of cricket field to football pitches including cut and fill. | Seddon Construction Limited | £2,554,099.00 | 20/10/2025 | 08/10/26 | Pagabo Framework Mini Competition | Large Enterprise | Plodder Lane, Edge Fold, Bolton, Lancashire, BL4 0NN | 03578140 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Regeneration | Multi-disciplinary team to develop RIBA stage 3 & 4 Planning & Tender Packs through to stage 5-6 Completion on site. | Pulse Associates Ltd Trading as Pulse Consult | £60,771.11 | 15/9/25 | 30/05/2027 | ESPO Direct Award | Medium Enterprise | The Birkin Building, Ground Floor Ten Broadway, Nottingham, England, NG1 1PS | 11619729 |
| Regeneration | Multi-disciplinary team to deliver RIBA 5-6 Services | Focus Consultants 2010 LLP | £188,694.26 | Sep-25 | Jun-25 | ESPO Direct Award | Medium Enterprise | 18 St Christopher’s Way, Pride Park, Derbyshire, DE24 BJY | OC357628 |
| Regeneration | Desktop Stats Study & On SIte Underground Services In Advance of site excavations | Premier Surveys Ltd | £5,040.00 | 30-Nov | 04-Dec | Single Quote <£10K | Small | 9 - 11 Lowater Street, Carlton, Nottingham, England, NG4 1JJ | 2389173 |
| Regeneration | Green Ashfield project carbon reduction project review in line with FMG quote 11025 dated 01/10/25 via email. | FMG Consulting Ltd | £6,400 | 17/12/25 | 03-Jan | Single Quote <£10K | Small | Bank House, Market Square, Congleton, Cheshire. CW12 1ET | 7309324 |

Discover Ashfield: Podcast

Suggested time frame: Ongoing with weekly, or bi-weekly uploads of the podcast  
Supporting team(s): Various, including health and wellbeing  
Priorities covered: Various.

OVERVIEW

The ‘Discover Ashfield Podcast’ looks to bring the history of Ashfield to life through engaging audio which aims to make the history of the district exciting and relevant.

Each episode will explore a different topic relating to the Ashfield Stories page through interviews and dynamic story telling from within our own community.

This project would not be a standard question and answer with a local historian, whilst that will form a small part of it, we believe the best way to bring this to life is to link in with local schools as part of a wider education programme, with school children conducting interviews, sharing facts and bringing stories to life through voice-based drama.

The first series will include eight topics / episodes exploring different themes, allowing for further scope to continue the project in the future, topics include.

- The first computer programmer – Ada Lovelace

- How collieries shaped the identity of Ashfield

- The literary genius inspired by Nottinghamshire’s landscapes – D H Lawrence

- The worlds first females Quakers minister – Elizabeth Hooton

- One of the greatest female cricketers – Enid Bakewell

- How industry brought rail stations to Ashfield

- The suffragettes in Sutton

- Looking to the stars: The Ashfield story

INTENDED OUTCOME(s)

- Promote the ‘Discover Ashfield’ brand in a previous unexplored way to varying audiences

- Bring the Ashfield Stories section to life through engaging audio and visual content

- Bring the Ashfield Stories section to life through educational workshops

- Drive more traffic to the DA website to encourage more footfall to Ashfield’s landmarks

- Create a lasting bank of historical educational content working with local schools

PRODUCTION AND PROMOTION

Production would be overseen and handled by Ashfield District Council, working collaboratively with our internal teams and external partners and providers. There will be some budgetary requirements for this to be brought to life, a detailed proposal will be created separately.

In terms of promotion, Ashfield District Council will promote this via our channels to an organic reach and will explore the possibility of paid partnerships (funded by DA) with Mansfield 103.2 to further promote the podcast via advertising and programming input.

TIMESCALE

This project will be a piece of long-term work with a loose time expectation of six months from conception to delivery.

February 2026 –Pitch to and decision from DA Board / start of pre-production

March, April, May 2026 – Production of eight podcasts working with local schools

June 2026 – Postproduction, launch of Podcast and promotion