# Kirkby Neighbourhood Board Minutes

# Date: Wednesday 21st October 2026

Time: 09:00 – 11:00

Venue: Urban Road and Microsoft Teams

Chair: Martin Rigley

| ATTENDEES |  |  |  |
| --- | --- | --- | --- |
| Name | Position on Board | Position/Organisation | Present |
| Martin Rigley | Chair | Project Manager, Alliance Procurement Solutions Ltd | P |
| Amy Fox | Board Member | Senior Marketing & Fundraising Manager, Portland College |  |
| Angela Bentley | Sub for Lee Anderson | MP Office |  |
| Angie Peppard Matt Pike | Board Member | Our Centre |  |
| Cllr James Walker-Gurley | Board Member | Council Member, representing Eastwood, for economic development and asset management |  |
| Cllr Matthew Relf | Board Member | Executive Lead Member for Growth, Regeneration and Local Planning, Ashfield District Council |  |
| Cllr Warren Nuttall | Board Member | Council Ward Member, Ashfield District Council |  |
| Daniel Howitt | Board Member | Head of Strategy & Performance, Police and Crime Commissioners Office |  |
| Dianne Holmes | Board Member | Head of Curriculum, Academy Transformation Trust Further Education (ATTFE) |  |
| Richard Gravelle | Board Member | Nottingham Trent University |  |
| Lee Anderson, MP | Board Member | MP for Ashfield and Eastwood |  |
| Libby MacKenzie | Board Member | Family Hubs |  |
| Louise Knott | Board Member | Vice Principal, West Notts College |  |
| Nina Bianco | Board Member | Kirkby Sales | P |
| Pauline Stojanovic | Sub for Angie Peppard | Our Centre | P |
| Pete Edwards | Board Member | Chair, Ashfield Health and Wellbeing Partnership | P |
| Peter Cribb | Board Member | District Manager, Inspire - Culture, Learning and Libraries | P |
| Peter Gaw | Sub for Peter Cribb | Chief Executive Officer, Inspire – Culture, Learning and Libraries |  |
| Roy Lewis | Board Member | KARA (Kirkby Area Residents Association) | P |
| Sarah Kirk | Board Member | Everyone Active | P |
| Simon Martin | Sub for Dianne Holmes | Vice Principal, Academy Transformation Trust Further Education (ATTFE) | P |
| Simon Morgan | Board Member | Everyone Active |  |
| Stephen Abson | Board Member | Coalfields Regeneration Trust | P |
| Teresa Jackson | Board Member | Trustee, Ashfield Voluntary Action | P |
| Tracey Bird | Board Member | Strategic Lead, Active Notts |  |
| Toby Metcalf | Substitute for Roy Lewis | KARA (Kirkby Area Residents Association) |  |
| Abbie Smith | Supporting Officer | Senior Communications Officer, Ashfield District Council |  |
| Alex Chapman | Sub for Paul Crawford | Graduate Regeneration Officer, Ashfield District Council |  |
| Andrea Stone | Supporting Officer | Wellbeing Manager, Ashfield District Council | P |
| Christine Sarris | Supporting Officer | Assistant Director – Planning and Regulatory Services | P |
| Emma Lindley | Supporting Officer | Housing Strategy Lead Officer, Ashfield District Council |  |
| Hollie Maxwell-Smith | Supporting Officer | Discover Ashfield Lead, Ashfield District Council |  |
| Jake Dalton | Supporting Officer | Communities Graduate, Ashfield District Council |  |
| Jenny Moody | Supporting Officer | Comms, Ashfield District Council | P |
| Lucy Lightfoot | Supporting Officer | Regeneration Officer, Ashfield District Council |  |
| Nicola Stevens | Supporting Officer | Policy and Place Investment - Economy and Growth Service at NCC | P |
| Paul Crawford | Supporting Officer | Investment Manager, Ashfield District Council |  |
| Sarah Daniel | Supporting Officer | Assistant Director - Regeneration, Ashfield District Council | P |
| Sarah Vaughan | Supporting Officer | Wellbeing Officer, Ashfield District Council | P |

| Agenda Item |  |
| --- | --- |
| 1 | Welcome / Introductions / Apologies – All |
|  | - Apologies received from Tracey Bird, Dianne Holmes, Cllr Matt Relph, Richard Gravelle, Liz Barrett, Libby Mackenzie; Tracey Horton, Peter Gaw, Paula Torres-Silver, Paul Crawford and Abbie Smith. |
| 2 | Minutes of last meeting and matters arising |
|  | - Peter Cribb declared an interest in the North Kirkby Gateway proposal because he works for Inspire. Pauline declared an interest in the gift-card item because Our Centre was a proposed recipient. |
|  | - The minutes of the previous meeting were reviewed and confirmed as an accurate record. |
|  | - Updates included: the Local Assurance Framework and financial due-diligence work would be covered later in the meeting; the Community Asset Survey had launched; support for Merry Stems allotments was progressing; Nina Bianco confirmed she had been added to the relevant town-centre subgroup; and the board branding update was deferred until the communications item. The electrical supply required for the Our Centre electric-vehicle proposal was reported to be insufficient, with an estimated £13,000–£15,000 upgrade cost, so alternative options were being considered. |
| 3 | Heritage, High Streets & Transport Subgroup - Previous meeting update - Project Proposal – North Kirkby Gateway |
|  | - The subgroup had appraised the North Kirkby Gateway library proposal and recommended it to the board. - The proposed relocation would place the library on the ground floor of the Ellis Street development, as part of a mixed-use scheme with housing above. - Reported benefits included a modern single-floor facility, wider services, improved accessibility and support for town-centre regeneration. |
|  | - Roy Lewis opposed the proposal, citing the nearly £1 million cost, pedestrian safety, the existing library’s central location, uncertainty over reuse of the existing building, floor-space comparisons and the applicant/funding structure. - Responses noted that the existing CLASP building was considered at end of life, still had asbestos risks, and that the new location was intended to support wider town-centre activity. - The board also agreed that the future of the existing library building and safe pedestrian access required further investigation. |
|  | - The board approved support for the North Kirkby Gateway library project. - Proposed by Teresa Jackson and seconded by Peter Edwards. - Roy Lewis requested that his vote against the proposal be recorded. |
|  | - Other subgroup updates included: Our Centre’s first-phase bus business case would proceed using two new diesel buses because the electric option was not currently viable; the Titchfield Park netball-court contract had been signed and pavilion planning application submitted; Chromebooks were expected for Year 10 Outwood Academy students in mid-November; the Community Facilities Survey was live; High Street Rental Auction work was progressing; and future opportunities included town-centre priorities, the historic railway footpath and smaller capital projects. |
|  | Actions: - Nicola Stevens to confirm the County Council’s intentions for the existing library building, including whether reuse or demolition is envisaged. - Nicola Stevens to follow up with Highways on pedestrian-safety concerns around access to the proposed new library. - Board members to encourage organisations needing premises to complete the Community Facilities Survey. |
|  | Safe & Happy Subgroup - Previous meeting update |
|  | - The Kirkby Family and Wellbeing Pilot had received seven tenders, which were due to be evaluated before returning to the board for approval. - Helping Kirkby Business and Enterprise was delivering one-to-one support and partners were asked to promote referrals. - Community Learning and Grants agreements were being issued; unsuccessful applicants had been signposted to alternatives; and first monitoring was planned for early January 2027. - Planning for the 2027/28 grant round had begun. |
|  | - The Trusted Spaces project had transferred to Hollie Maxwell-Smith and was progressing towards procurement. - The community engagement plan was being updated for submission by the end of October. - Positive updates were noted on Heart of the Hill, health walks, Discover Ashfield Awards and the Kirkby Careers Fair held on 14 October. |
|  | - Teresa Jackson asked for Ashfield Voluntary Action to be included under engagement through community hubs. - Nina Bianco offered to circulate business-support information to local businesses. |
|  | Actions: - Sarah Kirk to add Ashfield Voluntary Action to the community-hubs engagement section. - Safe and Happy / council officers to send business-support/grant information to Nina Bianco for circulation. - Andrea Stone / programme team to incorporate Stephen’s comments into the Community Engagement Plan and arrange submission. |
| 4 | Programme Governance and Updates - Local Assurance Framework - Project Progress - Risk Summary - Finance Update - Monitoring and Evaluation Update |
|  | - The revised Local Assurance Framework clarified decision-making, concept endorsement, PID development, initial accountable-body assessment, optional external assurance, subgroup review, handling of declared interests and final board ratification. - Teresa Jackson identified numbering errors on page 36, which were accepted for correction. |
|  | - The programme risk position was reported as stable, with mitigations in place. - Chair’s expenses of £95.90 for the Pride in Place Summit were noted. - The monitoring return, due 29 October, covered capacity funding, delivery and planned projects, and board membership changes. |
|  | - The board approved submission of the monitoring return. - Proposed by Teresa Jackson and seconded by Nina Bianco. |
|  | Actions: - Sarah Daniel / programme team to correct the numbering errors on page 36 of the Local Assurance Framework. |
| 5 | Comms & Engagement - Comms/branding Update - Engagement Plan |
|  | - The board reviewed the branding guidelines and raised no objections. - The draft Community Engagement Plan had been circulated; Stephen’s submitted comments would be incorporated before submission to central government by the end of October. |
|  | - The board approved submission of the Community Engagement Plan with Stephen’s comments incorporated. - Proposed by Peter Edwards and seconded by Sarah Kirk. |
|  | Actions: - No actions. |
| 6 | Any Other Business – All - Gift card – repurposing and redistribution to Kirkby organisations - Chair Summit Update - Ashwood Church – Project Update - Board – Membership and Away Day |
|  | - Six gift cards, each currently worth £42.80 and expiring in May 2028, were proposed for Kirkby Community Grocery, Ashwood Centre, The CRAG, The Acre, Our Centre and Evergreens. - The board agreed the proposed distribution. - It was noted that the cards were losing value over time. |
|  | - The Chair reported that government continued to see neighbourhood boards as community-led, with the council acting as accountable body. - The board would consider membership, community representation and possible “backbone organisation” models at its away day. - Government procurement guidance was expected before Christmas. |
|  | - Early approaches had been received concerning a proposed £3.2 million new church and from Ashfield Spartans Boxing Club. - Members discussed the need for clearer communication of available funding, annual programmes, timescales and eligibility. - There was support for proportionate requirements, early guidance to applicants and avoiding unnecessary work where no suitable funding route existed. - Smaller grants, normally around £5,000, could be handled through annual community grant rounds, potentially including limited capital items. - The board agreed to continue this discussion at the away day rather than add an immediate new expression-of-interest stage. |
|  | - The next board meeting will be held on 4 December 2026 and followed by a face-to-face away day of approximately two to three hours at a community venue. - Bentinck was suggested as a possible venue. |
|  | Actions: - Council officers to distribute the six gift cards to the agreed organisations. - Board landing page being developed by the Investment team, easy-read investment plan and clearer communications on funding availability, categories and timescales. - The funding/application pathway, proportional due diligence, support for applicants and small capital grants to be included on the away-day agenda. - Council to arrange the 4 December meeting and away day at a community venue, considering Bentinck. - Chair / council officers to continue reviewing board membership and representation; follow up the English Rose contact (Pauline) and a potential Bentinck representative. |
| 7 | Date of Next Meeting – Friday 4th December 2026 |