# Kirkby Neighbourhood Board Minutes

# Date: Friday, 06 March 2026

Time: 09:00 – 11:00

Venue: Microsoft Teams

Chair: Martin Rigley

| ATTENDEES |  |  |  |
| --- | --- | --- | --- |
| Name | Position on Board | Position/Organisation | Present |
| Martin Rigley | Chair | Project Manager, Alliance Procurement Solutions Ltd | P |
| Amy Fox | Board Member | Senior Marketing & Fundraising Manager, Portland College |  |
| Angela Bentley | Sub for Lee Anderson | MP Office |  |
| Angie Peppard | Board Member | Our Centre |  |
| Cllr Matthew Relf | Board Member | Executive Lead Member for Growth, Regeneration and Local Planning, Ashfield District Council | P |
| Cllr Warren Nuttall | Board Member | Council Member |  |
| Daniel Howitt | Board Member | Head of Strategy & Performance, Police and Crime Commissioners Office |  |
| Dianne Holmes | Board Member | Head of Curriculum, Academy Transformation Trust Further Education (ATTFE) | P |
| Katie Roberts | Board Member | General Manager, Kirkby Leisure Centre, Everyone Active |  |
| Kelvin Eatherington | Board Member | Enterprising Ashfield Project and Interim Economic Programme Manager, NTU | P |
| Lee Anderson, MP | Board Member | MP for Ashfield and Eastwood |  |
| Louise Knott | Board Member | Vice Principal, West Notts College |  |
| Mark Cawar | Board Member | Feather Partnership |  |
| Nina Bianco | Board Member | Kirkby Sales | P |
| Olivia Bestwick | Observer | HR Advisor, Van Elle |  |
| Pauline Stojanovic | Sub for Angie Peppard | Our Centre | P |
| Paul Dobson | Board Member | Training and Assessment Manager, Van Elle |  |
| Pete Edwards | Board Member | Chair, Ashfield Health and Wellbeing Partnership | P |
| Peter Cribb | Board Member | District Manager, Inspire - Culture, Learning and Libraries | P |
| Peter Gaw | Sub for Peter Cribb | Chief Executive Officer, Inspire – Culture, Learning and Libraries |  |
| Roy Lewis | Board Member | KARA (Kirkby Area Residents Association) | P |
| Sarah Kirk | Board Member | Everyone Active |  |
| Simon Martin | Sub for Dianne Holmes | Vice Principal, Academy Transformation Trust Further Education (ATTFE) |  |
| Simon Morgan | Board Member | Everyone Active |  |
| Stewart Nubley | Board Member | Ashfield Spartans Boxing Academy |  |
| Teresa Jackson | Board Member | Trustee, Ashfield Voluntary Action | P |
| Tracey Bird | Board Member | Strategic Lead, Active Notts | P |
| Toby Metcalf | Substitute for Roy Lewis | KARA (Kirkby Area Residents Association) |  |
| Abbie Smith | Supporting Officer | Senior Communications Officer, Ashfield District Council | P |
| Andrea Stone | Supporting Officer | Wellbeing Manager, Ashfield District Council | P |
| Christine Sarris | Supporting Officer | Assistant Director – Planning and Regulatory Services |  |
| Emma Lindley | Supporting Officer | Housing Strategy Lead Officer, Ashfield District Council | P |
| Hollie Maxwell-Smith | Supporting Officer | Discover Ashfield Lead, Ashfield District Council |  |
| Jake Dalton | Supporting Officer | Communities Graduate, Ashfield District Council | P |
| Jenny Moody | Supporting Officer | Comms, Ashfield District Council |  |
| Joelle Davies | Supporting Officer | Group Manager for Growth, Infrastructure and Development at NCC | P |
| Lucy Lightfoot | Supporting Officer | Business Support and Performance Lead, Ashfield District Council | P |
| Melanie Wheelwright | Supporting Officer | Service Manager - Economic Growth, Ashfield District Council | P |
| Paul Crawford | Supporting Officer | Investment Manager, Ashfield District Council | P |
| Sarah Daniel | Supporting Officer | Assistant Director - Regeneration, Ashfield District Council |  |
| Sarah Vaughan | Supporting Officer | Wellbeing Officer, Ashfield District Council | P |

| Agenda Item |  |
| --- | --- |
| 1 | Welcome / Introductions / Apologies – All |
|  | - Apologies received from Cllr. Walker Gurley, Libby McKenzie, Sarah Kirk, Christine Sarris, Liz Barrett, Mark Cawar, Louise Knott, Mark Yates, Amy Fox, and Steven Abson. |
| 2. | - Introductions from Nina Bianco and Jake Dalton. |
| 2 | Minutes of last meeting and matters arising |
|  | - Minutes approved as an accurate record. |
|  | - Local Assurance Framework – revisions completed (Sarah & officers). |
|  | - Digital project PIDs – examples circulated; blank template still to be shared if useful (Melanie). |
|  | - New membership requests – to be considered in today’s AOB; subgroup membership to be reviewed as needed. |
|  | - Residency/employment eligibility response – action had been logged for Sarah V; original context unclear and to be closed/clarified. |
|  | - Grant criteria & community grants – discussed under Safe & Happy update (Andrea). |
|  | - Reporting template & risk register – provided for March meeting (officers). |
|  | - Engagement materials – in progress (Officers & Abbie). |
|  | - Resident voice/housing groups linkage – in progress (Tracey). |
|  | - Linking new community groups to Board comms – to be covered in Comms & Engagement (Teresa input). |
|  | - LGR implications & guidance monitoring – ongoing (officers). |
|  | - December minutes (5th Dec) – discussed later in the meeting and approved |
| 3. | Programme update |
|  | - Awaiting formal feedback/approval from DLUHC/MHCLG; expectation remains for April readiness. |
|  | - Updated monitoring guidance requires a baseline monitoring exercise in April, focused on capacity funding spend and forecast; approach described as lighter touch than previous regimes. |
| 4. | Project proposals - Heritage, High Streets & Transport - Digital Inclusion - Morvern Park Play Zone - Titchfield Park |
|  | Digital Inclusion – Outwood Academy Kirkby (Pilot) - Proposal: Issue laptops to pupils entering Year 10 (from Sept 2026) to reduce digital poverty and improve study access; safeguarding/controls to be applied; potential broadband access/dongles to be explored. - Value: £78,451 over 2 years (grant to Outward Academy). - Discussion points: - Strong educational and aspiration benefits; device security and web-filtering manageable via school IT systems. - Concerns raised about universal allocation vs. targeting; sustainability beyond pilot; risk of loss/sale/damage; equity with other local schools. - Mitigations discussed: device tagging/locks, school ownership during 2-year study period, potential unlock at end; exploring match (e.g., Pupil Premium), potential corporate sponsorship if pilot is successful; options for returns/resale/bond incentives considered; no behaviour-based exclusion from access. - Decision: Approved (subject to overall programme funding being confirmed). One vote against recorded. Owner(s): Outward Academy & Officers to finalise PID/details. |
|  | Morven Park PlayZone (All-weather multi-use court near Morven School) - Need: Low activity levels, health inequalities, limited youth provision, ASB reduction. - Funding position: Football Foundation secured ~£249,999; Board asked to match with ~£99,999 (final figure to be confirmed in PID). - Operating model: Mix of activation-led sessions (with Sport England activation funding bid), low/no-cost community access, bookings by clubs (to build a maintenance reserve), and CCTV/security. Focus also on women & girls, disability & LTCs (grant conditions). - Decision: Approved in principle to provide match (subject to programme funding). Owner(s): Andrea/Tracey/Sarah V to progress including Sport England activation bid and pricing/booking plan. |
|  | Titchfield Park – Sports Pavilion & Courts - Scope: Replace life-expired pavilion; refurbish courts (tennis/netball). Bowls area excluded. Maintain bookings (clubs/teams) to support upkeep. - Funding: £591,588 (Pride in Place) requested; £9,726 pre-development match from Council already secured. - Decision: Approved in principle (subject to programme funding). - Owner(s): ADC officers (Paul C.) to progress design, security options and phasing. Note: All approvals above are subject to DLUHC/MHCLG confirmation of the main fund and eligibility to spend on these project types. |
| 5. | Terms of Reference Updates |
|  | - Decision: Updated ToR approved. |
|  | - Membership: Clarified difference between board members, observers, and named representatives who may attend on behalf of members. |
|  | - MP engagement: Requirement to involve local MP noted; challenge with availability also experienced on other town boards. to re-contact MP office to improve engagement/attendance. |
| 6. | Subgroup Updates - Heritage, High Streets & Transport Subgroup - Safe & Happy Subgroup |
|  | Heritage, High Street & Transport (Teresa Jackson) - Covered through agenda item 4 (three project proposals). - Future pipeline: e.g., Our Centre buses—a forthcoming proposal is expected from Pauline. |
|  | Safe & Happy (report by Andrea Stone on behalf of Sarah Kirk (Chair) Revenue programme – pipeline by theme - Community-based learning & development - Concept: Grants to support adult/community learning (e.g., family learning, community skills/health/wellbeing). - Initial scope: 4× £5,000 grants in Year 1. - Status: To be written up as a PID for next Board (Lead: Dianne Holmes with subgroup). - Child poverty intervention - Status: First-stage proposal in development for next subgroup (Lead: Nathan McNicolas; supported by Pete Edwards, Libby Mackenzie, and Sally Bestwick). - Community cohesion – Grants programme - Status: Criteria & application drafted; minor tidy-up; PID to next Board (Lead: Andrea Stone) - Health & Wellbeing (connecting residents to local assets/services) - Concept: Support/Link Worker to strengthen referral/participation in existing Kirkby assets/services. - Leads: Tracy Bird, Emma Lindley, Sally Beswick. - Status: Proposal drafted; to next subgroup, then PID to Board. - Work, Productivity & Skills - Approach for Y1: Prioritise 1:1 tailored support for local businesses (relationship-led), with other elements considered later. - Leads: Melanie Wheelwright and Paul Stoppard; PID to next Board. - Anti-social behaviour - Status: Initial proposal in development (Lead: Sean Beastall) for next subgroup. Coordination / Collaboration notes - Teresa flagged alignment with Ashfield Voluntary Action’s community-led empowerment programme (groups on several estates). Action: subgroup to connect proposals/grants to existing estate groups (Dianne/Andrea to link with AVA/Una). Next Safe & Happy subgroup: ~23 March 2026 |
| 7. | Finance Update |
|  | - Main Programme: Awaiting DLUHC/MHCLG approval. |
|  | - Capacity Funding: No new spend since last meeting; upcoming approved spend to Abbey Hill School. |
|  | - Profiles: Funding profiles included in the board pack. |
|  | - Clarifications: - Unspent capacity funding in FY 25/26 will be reprofiled to future years (expenditure plans come back to Board). - Capacity funding is included in the £20m programme; spreadsheet displays will be updated to avoid confusion. |
| 8. | Comms & Engagement |
|  | - Pre-announcement posture: Hold major comms until funding approval lands; then announce early projects and show alignment with previous consultation insights. |
|  | - Business/community updates: Preference for a short 2-page newsletter (plain English highlights) rather than circulating full board packs. |
|  | - Branding/strapline: Explore a positive, resident-facing banner (e.g., “Let’s Go Leamington”) to unify Kirkby regeneration activity across funds. To be discussed at next Safe & Happy subgroup; ideas welcome to Andrea/Abbie. |
|  | - Action: Abbie/Comms to bring a short presentation/proposal (newsletter approach + strapline options) to next Board. |
| 9. | Any Other Business – All - Board paper circulation - MHCLG Survey |
|  | Business/Stakeholder Engagement - Mansfield Building Society (Kirkby branch): interested in staying informed but cannot commit to board role now; supports regular updates. - Nina Bianco: requested better notification of town events (e.g., Christmas Fair); supports the 2-page update idea. - Potential new/returning organisations: - Outwood Academy Kirkby – principal keen to engage (already referenced). - English Rose – business contact previously provided. - Citizens Advice – Sally Beswick expressed interest (board or Safe & Happy). - Discover Ashfield Award winners from Kirkby to approach (Andrea to supply list to Martin): e.g., Swit Swoo, Lux 360 Booths, Matthews & Tannert, Ashfield Evergreens, Showstoppers (and others as appropriate). - Board size balance: keep Board representative but avoid top heavy membership; use subgroups for broader involvement. - Action: Andrea to share award winner list with Martin; Martin (and officers) to sound out prospects before next meeting and return with recommendations. |
|  | Twinning with Ronchin (France) – Cllr. Matt Relf - Longstanding twinning link underused; strong cultural/industrial parallels. - Action: Interested members to contact Matt Relf; Matt to report back next meeting on options to revitalise the link (e.g., arts/schools/sport). |
|  | Zencity Sentiment Survey (DLUHC-commissioned) - Latest sample n=111; summary available (ask officers); broadly reaffirms known issues/opportunities. - Action: Officers can share full report on request (40 pages). |
|  | Community-led delivery / CIC expectations - DLUHC to issue further guidance in coming months; no blanket requirement to convert to CIC, but models under consideration. - Support offer: Teresa Jackson / Ashfield Voluntary Action can advise groups on structures (CIC/CIO/SPV). |
|  | McDonald’s (Lane End) planning query (Heritage subgroup) - Update: Application undetermined; highways response awaited. Any site clearance seen is landowner maintenance, not development start. |
|  | Staffing - Joelle (Joel) Davies is leaving NCC for Greater Lincolnshire CCA at end of April; replacement TBC and to be notified. |
|  | Minutes of 5th December meeting reviewed on screen and approved as accurate. |
|  | Decisions Summary - ToR: Approved. - Projects approved in principle (subject to programme funding): - Outwood Academy Kirkby – Digital Inclusion Pilot (£78,451) – approved (1 vote against). - Morven Park Play Zone – provide ~£99,999 match to £249,999 Football Foundation grant – approved in principle. - Titchfield Park Pavilion & Courts – £591,588 plus £9,726 Council pre-dev match – approved in principle. |
|  | Minutes approved: 28th Jan and 5th Dec. |
| 10. | Date of Next Meeting – Wednesday 15th April 2026 |